## Procurement Plan
Schedule Item | Description | UoM | Quantity | Procurement Method | Est. Publication Date | Est. Award Date | Est. Start Date
1000 - Ammonium nitrate explosives | For underground mining blasting, ore excavation | Box | 12000 | direct | 2026-04-01 | 2026-05-01 | 2026-06-10
1000 - Cement | Special for underground waterproof grouting, for surrounding rock seepage prevention and water inflow control | Tonnes | 8000 | direct | 2026-01-01 | 2026-01-10 | 2026-01-15
1000 - Fuels, oils and lubricants | Mining Equipment Vehicle Fuel and Mining Equipment | Litres | 400000 | db | 2026-01-03 | 2026-01-13 | 2026-01-23
1000 - Fuels, oils and lubricants | Special Lubricants for Mining Equipment | Drum | 50 | direct | 2026-02-01 | 2026-02-20 | 2026-03-05
1000 - Lime | Auxiliary Consumables for Copper Ore Processing Plant | Tonnes | 175 | direct | 2026-04-28 | 2026-05-10 | 2026-05-20
1000 - Nitric acid | Chemical Reagents for Processing Plant Laboratory | Litres | 150 | direct | 2026-04-29 | 2026-05-20 | 2026-06-15
1000 - Sulphuric acid | Chemical Reagents for Processing Plant Laboratory | Litres | 80 | direct | 2026-04-29 | 2026-05-20 | 2026-06-15
1000 - Hydrochloric acid | Chemical Reagents for Processing Plant Laboratory | Litres | 150 | direct | 2026-04-23 | 2026-05-10 | 2026-06-15
1000 - Ammonia | Chemical Reagents for Processing Plant Laboratory | Litres | 150 | direct | 2026-02-23 | 2026-03-01 | 2026-03-15
3000 - After-sales services | After-sales Services for Engineering Equipment, etc. | Service | 5 | ncb | 2026-01-13 | 2026-01-25 | 2026-02-10
3000 - Electricity | Mining Area Power Supply | Kilowatt | 52131150 | direct | 2026-01-01 | 2026-01-10 | 2026-01-20
2000 - Food | Daily Catering for Mining Area | Kg | 36000 | direct | 2026-01-10 | 2026-01-20 | 2026-02-01
2000 - Furniture | Living or Office Supplies | Set | 50 | direct | 2026-02-10 | 2026-02-23 | 2026-02-27
2000 - Medicines | Materials for Mining Area First Aid Station or Emergency Rescue | Box | 300 | ncb | 2026-01-14 | 2026-01-25 | 2026-02-10
2000 - Office equipment | Office Supplies | Set | 150 | direct | 2026-02-10 | 2026-02-23 | 2026-02-27
3000 - Engineering services | engineering services and material costs and mill renovation project. | Cubic Metre | 170000 | direct | 2026-01-01 | 2026-01-10 | 2026-01-15
3000 - Engineering services | SURFACE CIVIL WORKS | Service | 10 | direct | 2026-08-01 | 2026-09-07 | 2026-09-15
2000 - Iron and steel products | engineering renovation projects and Processing Plant | Tonnes | 30 | ncb | 2026-06-10 | 2026-07-10 | 2026-07-20
1000 - Mining equipment and machinery spare parts | Loader and excavator batteries | Set | 3 | direct | 2026-01-05 | 2026-01-15 | 2026-01-25
1000 - Mining equipment and machinery spare parts | Backfilling Station Construction and Other Mine Auxiliary Equipment | Set | 20 | icb | 2026-01-05 | 2026-01-15 | 2026-01-25
1000 - Forged mill balls | Steel balls for the concentrator plant | Tonnes | 505 | ncb | 2026-08-01 | 2026-08-15 | 2026-09-10
1000 - Centrifugal pumps | Mining equipment | Set | 1 | icb | 2026-01-01 | 2026-01-05 | 2026-01-10
1000 - Electrical switch boxes | Locally purchased hardware in Zambia | Set | 1 | direct | 2026-02-02 | 2026-02-15 | 2026-02-26
1000 - Mining equipment and machinery spare parts | Gas for steel welding, cutting and machining consumables | Each | 220 | direct | 2026-01-05 | 2026-01-15 | 2026-01-20
1000 - Mining equipment and machinery spare parts | Jack | Set | 1 | direct | 2026-01-15 | 2026-02-10 | 2026-03-01
1000 - Mining equipment and machinery spare parts | Loader ZL50CN | Set | 2 | direct | 2026-09-15 | 2026-09-25 | 2026-10-05
3000 - Drilling and blasting | Water Well Drilling Service for Residential Area | Each | 2 | ncb | 2026-01-15 | 2026-01-25 | 2026-02-01
1000 - Low and medium voltage electric cables | Electrical power lines for mine living quarters and production | Metres | 6000 | ncb | 2026-01-03 | 2026-01-13 | 2026-01-20
3000 - Dewatering | HDPE Pipe for Mining Water Supply & Drainage | Metres | 600 | ncb | 2026-02-02 | 2026-02-14 | 2026-02-27
1000 - Drive shaft, gears and nuts and bolts | Materials for mine water supply and drainage | Each | 2500 | direct | 2026-02-02 | 2026-02-14 | 2026-02-27
1000 - Ball and gate valve | Materials for mine water supply and drainage | Each | 50 | direct | 2026-02-02 | 2026-02-14 | 2026-02-27
1000 - Low and medium voltage electric cables | ARMOURED CABLE,TERMINATION KIT AND JOINT | Each | 40 | direct | 2026-01-15 | 2026-01-25 | 2026-02-01
1000 - Mining equipment and machinery spare parts | Graphite Packing for pump | Roll | 10 | direct | 2026-03-01 | 2026-05-15 | 2026-05-28

## ScheduleData (hidden)
1000 - Activated carbon | Acre | icb
1000 - Aluminum conductors | Ampere | db
1000 - Ammonia | Bag | rfp
1000 - Ammonium nitrate explosives | Bar | ti
1000 - Ball and gate valve | Barrel | eoi
1000 - Bearing housings | Becquerel/Kilogram | pq/pqq
1000 - Brake shoes | Bll Barrel (Petroleum) (158,987 Dm3) | ss
1000 - Bronze bushes | Block | others
1000 - Carbon brushes | Bottle | ncb
1000 - Caustic soda | Box | direct
1000 - Cement | Bundle
1000 - Centrifugal pumps | Can
1000 - Coal | Candela
1000 - Conveyor belt idlers | Cap
1000 - Copper rod, copper shapes and bus bars | Carat
1000 - Couplings and nozzles | Cell
1000 - Crane wheels | Centimetre
1000 - Crusher wear plates | Count
1000 - Drive shaft, gears and nuts and bolts | Cubic Centimeter
1000 - Electrical switch boxes | Cubic Centimeter/Second
1000 - Enamel wire electric motors | Cubic Decimeter
1000 - Feeder wear plates | Cubic Metre
1000 - Ferrosilicon | Day
1000 - Forged mill balls | Dekalitres
1000 - Forged roof bolts and nuts | Dozen
1000 - Fuels, oils and lubricants | Drum
1000 - High chrome and low chrome | Dry Metric Tonnes
1000 - High density polyethylene pipes | Each
1000 - Hydrochloric acid | Engine Capacity
1000 - Iron and steel intermediate products | Feet
1000 - Jack hammers | Gallon
1000 - Lime | Gigaohm
1000 - Low and medium voltage electric cables | Gram
1000 - Low and medium voltage transformers | Gram/Cubic Meter
1000 - Low- and high-tension ceramic insulators | Gross
1000 - Mild steel and high tensile nuts and bolts | Hectare
1000 - Mill chutes, tanks and steel | Hour
1000 - Mill liners | Hundred Kilowatt Hours
1000 - Mining equipment and machinery spare parts | Inches
1000 - Nitric acid | Kg
1000 - Overhead and moving crane | Kilogram/Cubic Decimeter
1000 - Pump housing | Kilometre
1000 - Pump impellers | Kilomol
1000 - Railway turnouts and accessories | Kilonewton
1000 - Refractory bricks and mortar | Kilowatt
1000 - Rock drills, drill bits and drill steels | Link
1000 - Safety equipment | Litres
1000 - Skip shoes | Lot
1000 - Slippers for cages | Meganewton
1000 - Soda ash | Megavolt
1000 - Sodium hydrosulphide | Megawatt Hour (1000 Kw.H)
1000 - Sodium silicate | Megohm
1000 - Sulphuric acid | Metal Per Cent (Grade) Of Ag - Silver
1000 - Underground flat cars | Metal Per Cent (Grade) Of Au - Gold
1000 - Vehicles for moving explosives | Metal Per Cent (Grade) Of Co - Cobalt
1000 - Wire bars, wire and nails | Metal Per Cent (Grade) Of Cu - Copper
3000 - After-sales services | Meter/Minute
3000 - Bulk transportation | Metres
3000 - Consultancies on core goods and services | Microampere
3000 - Dewatering | Microfarad
3000 - Drilling and blasting | Microliter
3000 - Electricity | Miligrammes
3000 - Engineering services | Millifarad
3000 - Geological and geotechnical services | Milligram
3000 - Medical services | Millilitre
3000 - Metal fabrication | Millimetre
3000 - Mine development | Minutes Of Air Time
3000 - Shaft sinking | Mol Per Cubic Meter
3000 - Wastewater treatment and disposal services | Mol Per Liter
2000 - Business cards and name | Month
2000 - Catering | Nanoampere
2000 - Catering equipment | Nanofarad
2000 - Cleaning materials and toiletries | Newton/Square Millimeter
2000 - Food | Number
2000 - Food supplies | Ounce
2000 - Furniture | Pack
2000 - Gardening | Packet
2000 - Iron and steel products | Pair
2000 - Labour | Pallet
2000 - Medicines | Part Per Thousand
2000 - Office equipment | Per One Hundred
2000 - Safety wear | Per Ten
2000 - Stationary | Pieces/Item [Number]
2000 - Uniforms | Pikofarad
4000 - Accommodation and camp management service | Pints
4000 - Bulk transportation services | Plate
4000 - Capacity building and training services | Pound
4000 - Catering services | Quarts
4000 - Cleaning and laundry services | Quintal
4000 - Consultancies in non-core goods and services | Reel
4000 - Corporate social responsibility consultancies and services | Roll
4000 - Excavation services | Service
4000 - Freight forwarding, logistics management, warehousing and storage services | Set
4000 - Haulage of fuel, consumables and personnel | Sheet
4000 - Haulage of ores, concentrates and refined metals | Square Centimetre
4000 - Information systems, information technology and communication | Square Feet
4000 - Labour hire – both specialised and non-specialised services | Square Metre
4000 - Legal and financial services | Square Yards
4000 - Management of municipal of waste | Tonne (Metric Ton)
4000 - Medical services | Tonnes
4000 - Municipal waste management | Tube
4000 - Painting, disinfection and fumigation services | Units
4000 - Physical training, gym and swimming services | Week
4000 - Plumbing works and other sanitary services | Yard
4000 - Provision of local health education services | Year
4000 - Provision of minor maintenance services
4000 - Provision of minor maintenance services such as electrical fittings
4000 - Safety, protection, firefighting system services
4000 - Security and patrol services
4000 - Supply base, warehouse, and storage services
4000 - Transportation of personnel

## Instructions
PROCUREMENT PLAN UPLOAD INSTRUCTIONS
This template includes dropdown menus for Schedule Item, UoM, and Procurement Method.
Click on any cell in these columns to see the dropdown arrow.
Field | Description
Schedule Item | REQUIRED. Select from dropdown. Format: 'Code - Name' (e.g., '1000 - Mining Equipment')
Description | REQUIRED. Description of the procurement item (text, not numbers)
UoM | REQUIRED. Select from dropdown: Units, Each, Kg, Litre, Service, Month, etc.
Quantity | Optional. Quantity to procure (number, 0 or blank if not applicable)
Procurement Method | Optional. Select from dropdown: icb, db, rfp, ti, eoi, pq/pqq, ss, others, ncb, direct
Est. Publication Date | Optional. Date when tender will be published (DD/MM/YYYY). Must be within reporting period
Est. Award Date | Optional. Expected date for contract award (DD/MM/YYYY). Must be within reporting period
Est. Start Date | Optional. Expected start date for contract/service (DD/MM/YYYY). Must be within reporting period
SCHEDULE ITEM CODE REFERENCE:
1000 - [Name] | Core Good - Mining-specific goods required for core operations (First Schedule)
2000 - [Name] | Non-Core Good - General goods not specific to mining operations (Second Schedule - 100% local)
3000 - [Name] | Core Service - Mining-specific services required for core operations (First Schedule)
4000 - [Name] | Non-Core Service - General services not specific to mining (Second Schedule - 100% local)
PROCUREMENT METHOD REFERENCE:
icb | Open tendering process inviting international suppliers to compete
db | Direct Bidding
rfp | Request for Proposal
ti | Tender Invitation
eoi | Expression of Interest
pq/pqq | Pre-Qualification Questionnaire
ss | Single Source / Sole Source
others | Other
ncb | Open tendering process restricted to nationally registered suppliers
direct | Direct award to a specific supplier without competitive tendering
VALIDATION RULES:
- Schedule Item, Description, UoM are required fields
- Quantity is optional (plan estimated value is set at plan level)
- Dates must be in DD/MM/YYYY format and within the selected reporting period
- Description cannot be a number
- Do not leave required cells blank
TIP: For Split Award procurements, use the Split Award Template from the portal.